## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Simplicity Issues | 8 | 20 | 160 | 2023-03-23 |  | A | Will get help at office hours or lab if this happens
Can't work at all over spring break | 40 | 2 | 80 | 2023-03-23 | 2023-04-02 | R | I didn't have time to work but I will still be able to finish on time
Troubles with physics model will delay other parts | 20 | 13 | 260 | 2023-04-05 | 2023-04-12 | M | I mitigated this by taking on the bulk of the physics task work this week
I have to present my demo early | 20 | 20 | 400 | 2023-04-20 |  | O | I will plan to get ahead in case my demo is early
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100